1 year prior		Determine which type of race and where

Work up a projected budget

Develop a prize list

Develop a sponsorship plan. Identify potential sponsors, levels of sponsorship and recognition they would receive.

Develop a marketing plan. What advertising, marketing mix and publicity you will use. Decide on media partners and delivery methods (broadcast, print, web/email medias)

September of year prior	Put your race on the next year’s OBRA schedule along with other cycling publications (print, web and email lists)

Submit dates and general race information to local chambers, visitor and recreation calendars.

6 months prior		Reserve your course and facilities

If the course is new then the course needs to be reviewed by an official appointed by OBRA.

Contact the municipalities/road use authorities about road approval/closure

Develop road plan (map course and distribution of volunteers

Develop a communications plan if needed, ex. If race needs to rent cell phones or professional radios

Outline a draft of a race flyer

Set up online registration

Develop a media plan, who and what media you will contact, etc

3 months prior 	Develop your race announcement/flyer. After completing approved flyer email to various cycling lists at least once a month, plus reminder week before race.

Develop a race website if needed

Announcement/flyer must be reviewed by OBRA prior to publication

Schedule your distribution of the flyer and/or advertisements

Start developing volunteer positions, time schedules and placement volunteers

Arrange for state certified flaggers if needed

45 days prior		File your OBRA insurance paperwork

Notify law enforcement and EMS personnel of the date of the event

Notify land owners/businesses along course of event

Arrange for First Aid provider (OBRA will schedule if requested)

Develop race info (race bible)

Start recruitment of volunteers

1 month Prior	Distribute insurance endorsements and confirm course reservations

Reserve course signage, equipment, port-a-potties

Confirm appointment of Officials

Send press releases to media by email or fax. Contact media by phone to develop stories or suggest story ideas relating to your event.

1 Week prior	Discuss event with Chief Official review budgetary constraints

Confirm port a potties

Email race flyer and updates out to various cycling lists.

Arrange parking facilities

Verify volunteers

Send press releases again to media my email or fax. Contact media and confirm stories, interviews and coverage of event.

Arrange meals/lunches for officials/volunteers

Days Prior			Pick up equipment, truck, etc.

Get change for cash box

Review necessary forms (entry forms, releases, start lists, results forms) and make needed copies

Obtain safety pins

Develop signage for registration

Fill water containers

Purchase and assemble snacks/lunches/drinks for volunteers and officials

Charge batteries in radios and display clocks, if multi day race

Morning of Race		Set up signage for course

Designate Warm up Area

Set up start-finish line/registration/results areas

Coordinate with Volunteer coordinator

Confirm with Chief Referee

Have Fun!

Keep mental or written notes of what is working and what is not

Thank volunteers, racers and officials

Post Race	Thank Everyone! Compose a general volunteer letter to send to all volunteers. Possibly write special thank you notes to officials.

Collect feedback from officials, and volunteers

Email or fax results, stories and race reports to media and email lists.

Celebrate the success of the event!

Volunteers Guidelines:
Corner marshals for time trial and road race
Lead and follow vehicles for road race
Registration workers

Course set up and take down

Basic Sponsors/Prizes Guidelines:
Create a Packet (Letter, Race flyer, Race Bible, Estimate participation, etc.)
Title Sponsor

Media Partners or Sponsors
Obtain sponsorship for local businesses
Gather race prizes
Thank you letter to all Sponsors

Publicity Guidelines:
Race Flyer

Race Press Releases
Race Bible
Distribution of Race Flyer
Getting event placed on race calendars

Budget:
Prize list of $__________
Estimated Rider attendance _____
Sponsorship/Advertising income of $_____________
Entry fee of $________
Late fee from ___% of the riders

Income:

Entry fee 	$

Sponsors 	$

Late fees 	$

Total Income 	$

Expenses:

Race Permit 	$

Insurance 		$

Late fees 		$

Police	 	$

Prizes 		$

Advertising 	$

Printing 		$

Equipment rental  $

Officials	 	$

Refreshments 	$

Trophies 		$

Total Expenses 	$

Net Profit 	$